## Summary Results
Details | Info | Type | Priority | Platform | Version When Tested | Status | Attachment | Dev remarks/question | QA Checking Attachment | QA Status
Forgot Password | Error prompts after submitting password (Password is changing, there is just an error prompt and the form fields are not clearing) | Bug Report | P1 | IOS, Android | 1.1.1 | To-do | Forgot Password Checking.mp4 |  | The issue here only applies for error prompt, but the password has been changed successfully
Login | When i logged in, it is only showing me a gray screen | Bug Report | P1 | IOS | 1.1.1 |  | (IOS) Can't continue to login
Sign up | Not signing in (Showing Error Message) | Bug Report | P1 | Web Admin |  |  | Web Sign up (Issue).mp4
Payment Dispute Viewing | Requested Payment Dispute not Showing | Bug Report, Pending/Ongoing Feature | P1 | Web Admin |  |  | Payment Dispute not showing.png
Forgot Password | Forgot Password Not Working on Email sent | Bug Report | P1 | Android | 1.2.4 | Done | Forgot Password from Mobile not working.mp4 |  |  | Passed
Check-In | Bottom navigation bar missing after checking-in | Bug Report | P1 | Android | 1.2.4 |  | bottom navigation bar went missing after checking in.webm
Add new Employee | Displaying: Error Verifying Account Instead of other page but the default password is working | Bug Report | P1 | Email Verification |  | Done | Email Verification Unsuccessful.png (Mobile) Email Verification Unsuccessful |  | (Fixed) Employee Email Verification.mp4 | Passed
Special Holiday | Special Holiday computation not working | Bug Report | P1 | Web Admin |  | Done | Special Holiday Not Working on PaySlip.mp4 |  |  | Passed
Adding Benefits and Allowance | Added Benefits and Allowance not Showing/Working | Bug Report | P1 | Web Admin |  |  | Add Benefits and Allowance Not Working (My Org Tab).mp4
Register your organization | No error message if the entered details are existing already in the system | Feature Request | P2 | Web Admin
Upload Employee Documents | Upload button not working | Bug Report | P2 | Web Admin |  |  | Upload Document button not working on Members Tab.mp4
Download Employee Document | Download button not Working | Bug Report | P2 | Web Admin |  |  | Download Employee Document Not Working.mp4
Add New Departments | Adding New Departments Not Working | Bug Report | P2 | Web Admin |  |  | Adding New Departments Not Working.mp4
Change Shift | Change Shift Not Showing | Bug Report, Pending/Ongoing Feature | P2 | Web Admin |  |  | Change Shift not Showing.png
My Organization (Deduction) | Can click save without adding description | Bug Report | P2 | Web Admin |  |  | Can click submit without description (Deductions).mp4
My Organization (Employee Doc) | Can click save without adding Title | Bug Report | P2 | Web Admin |  |  | Can click save without title (Employee Doc).mp4
My Organization (Holidays) | Can click save without adding required fields | Bug Report | P2 | Web Admin |  |  | Can click save without required fields (Holiday).mp4
Deductions | Delete button not working | Bug Report | P2 | Web Admin |  |  | Deduction Delete button not working.png
Create New Post | Name is still static | UI | P3 | Android | 1.2.4 |  | (Android) Static Name.png
Close Button on Employee Side | Close Button is not working but the close icon is working. This applies to: (Members Tab) - Add Deduction and Edit Deduction Form - Add Benefits and Edit Benefits | Bug Report | P3 | Web Admin |  |  | Close Button Not Working.mp4
Salary List Viewing | UI: Title Header is Leave Request instead of Salary List | UI | P3 | Web Admin |  | To-do | Salary List Title.png
Verify Email content | After adding the employee. When email verfication has been sent and clicked 'confirm email', it navigates to the old URL. | Bug Report | P1 | Email Verification |  | Done | Old url nav for email confirmation.mp4 |  | (Fixed) Employee Email Verification.mp4 | Passed
Adding Benefits | Add Deductions Label Instead of Add Benefits | UI | P3 | Web Admin |  |  | Add Deductions instead of Add Benefits Text.png
Email verification | No verification email has been sent to the email of the added employee | Bug Report | P1 | Android | [5 empty] | Passed
Once a half-day leave has been filed for a half-day absence, any late by the employee is not counted in the UT. | Late is still counted in the UT even if half-day leave has filed | Bug Report | P1 | Web Admin |  |  | Half-day UT computation in filed half-day leave issue.mp4

## EARLEE REVALIDATION RESULT (CLI
Details | Client Attachment | Status | Category | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
A separate line was added for half-day pay, but the full-day pay was still included in the standard pay section of the payslip. This caused the total gross pay to be overstated. Refer to the link below for the illustration. | https://1drv.ms/v/s!AgzDKDqWI8SdncAkehIPlPLKfFJTEw?e=6Cf9Fy | Pass | Issue | P1 | standard pay also displayed and being added to the total gross pay instead of half day pay only(FIXED).mp4 | FIXED as of June 11 2025 |  | 2025-06-17
The following pay periods were tested: 1. Daily - wrong standard pay calculation 2. Semi-monthly fixed - unable to generate payslip 3. Monthly fixed - unable to generate payslip 4. Weekly - working 5. Semi monthly -working 6. Monthly - working | https://onedrive.live.com/?qt=allmyphotos&photosData=%2fshare%2f9DC423963A28C30C!484618%3fithint%3dvideo%26e%3d6uVlQX&sw=bypassConfig&cid=9DC423963A28C30C&id=9DC423963A28C30C!484618&authkey=!AHF4kdbKO2EqERk | FOR QA | Issue | P1 | cant generate payslip to several pay periods.mp4 |  | Can now generate monthly and semi monthly fixed | 2025-06-17
Important: Please add an adjustment field where all adjustments can be entered as a work around if an error in the calc arises or while you finalize some issues affecting the calculation | Adjustment field.png | Pending | Feature Request | P1 |  | The client want this feature request to be prioritized | API is completed but need to integrate by front end
Reset button in the attendance tab (in the portal) is not working | https://1drv.ms/v/s!AgzDKDqWI8SdncAjFM3COhJq5e61Qg?e=cIwyUg | Pending | Issue | P2 | reset form is working but update button isnt | reset button is working, but the update button is not after resetting - When user click reset button Then the attendace logged will reset and displays No time in and no time out | For Web dev | 2025-06-17
Not able to register and log in using Iphone | Registration in Apple.jpg | Pending | Issue | P1 | iOS login not working | stucked at loading after logging in with correct credentials | For mobile dev | 2025-06-17
Change password displays an error but it actually pushes through | https://1drv.ms/v/s!AgzDKDqWI8SdncoLjL-4guNfJEqaVg?e=iijJcz | FOR QA | Issue | P1 | Reset password.mp4 | The password change doesn't push through. It is a total error because the password has not been changed at all | For Web dev, no error on API, must check by Alphonso Velarde | 2025-06-17
No year 2025 in the dropdown in mobile app (for leaves, OT history display) | https://1drv.ms/i/s!AgzDKDqWI8SdncAl41sD2nHD6UYmqw?e=ii2tiu | Pending | Issue | P2 | No year 2025.mp4 | There is no year 2025 in the dropdown | For mobile dev | 2025-06-17
Details | Client Attachment | Status | Category | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
For new company registration, features not working: Bulk upload of employees | Bulk upload.mp4 | Pass | Issue | P2 | bulk upload employee now working.mp4 | bulk upload fixed | This has been retest , bulk upload is working please use the correct template. I sent it on the slack | 2025-06-10
Upload company logo not working - confirmed working but there is an error pop up notification | company logo.png | Pass | Issue | P2 | company logo.mp4 |  |  | 2025-06-10
Wrong total in payslip (SSS deduction was not considered) - confirmed working |  | Pass | Issue | P1 | wrong net pay calculation was fix.mp4 |  |  | 2025-06-10
Undertime not considered in computing for SSS for 2nd cutoff - calc is working but has a major issue in the payslip generation - The error in this issue lies in the Undertime in the 2nd cutoff payslip. - 2nd cutoff payslip still shows the UT from the 1st cutoff. - This affects the calc of SSS deduction for the 2nd cutoff payslip (calc with the correct UT vs. calc with the UT shown in the payslip) | Undertime.mp4 | Pass | Issue | P1 | Under time.mp4 | There is an undertime deduction even though the employee works full time for those certain days. | This has been fixed, while still on pending status ? | 2025-06-10
Please add the ceiling for Philhealth contribution. This should be 2.5% of P100,000.00 (maximum salary) per month - confirmed working |  | Pass | Issue | P1 | PhilHealth deduction.mp4 |  |  | 2025-06-10
Half day leave filed does not show half day in the portal | Half day leave.png | Pending | Issue | P2 |  |  | This is for front end, api is returning if it is half day
Payslip tab is not visible | UI | Pass | Issue | P3 | payslip tab is not visible (FIXED).mp4 | Fixed. Dev added an arrow slider to navigate the tab |  | 2025-06-13
Not able to register and log in using Iphone | Registration in Apple.jpg | Pending | Issue | P1 | iOS login not working | stucked at loading after logging in with correct credentials | For mobile dev
Pop up error notif in setting up the company details | Pop up error.png | Pass | Issue | P3 | error pop-up.mp4 | No errors pop up |  | 2025-06-10
Half day work is presented as whole day work less half day undertime. This should be presented as half day work with no undertime |  | FOR QA | Issue | P2
Wrong Philhealth minimum amount. This should be P250 per month | PHIC min amount.png | Pass | Issue | P1 | philhealth.mp4 |  | This has been corrected, when salary is below 10000 , the philhealth amount is 250 per month | 2025-06-10
Change password is not available on mobile app | https://1drv.ms/i/s!AgzDKDqWI8SdncAoEVwCunNO8BXg5g?e=SFKq0Z | Pending | Issue | P1 | change pass in mobile error.jpg |  | For mobile dev
No year 2025 in the dropdown in mobile app (for leaves, OT history display) | https://1drv.ms/i/s!AgzDKDqWI8SdncAl41sD2nHD6UYmqw?e=ii2tiu | Pass | Issue | P1 | Year 2025 is available in the dropdown in mobile app (for leaves, OT history display).jpg | Year 2025 is available in the dropdown |  | 2025-06-10
Details | Client Attachment | Status | Category | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
Upload company logo not working - confirmed working but there is an error pop up notification | company logo.png | Pass | Issue | P2 | company logo.mp4
Wrong total in payslip (SSS deduction was not considered) - confirmed working |  | Pass | Issue | P1 | wrong net pay calculation was fix.mp4
Undertime not considered in computing for SSS for 2nd cutoff - calc is working but has a major issue in the payslip generation - The error in this issue lies in the Undertime in the 2nd cutoff payslip. - 2nd cutoff payslip still shows the UT from the 1st cutoff. - This affects the calc of SSS deduction for the 2nd cutoff payslip (calc with the correct UT vs. calc with the UT shown in the payslip) | Undertime.mp4 | Pass | Issue | P1 | Under time.mp4 | There is an undertime deduction even though the employee works full time for those certain days. | This has been fixed, while still on pending status ? | 2025-06-03
Please add the ceiling for Philhealth contribution. This should be 2.5% of P100,000.00 (maximum salary) per month - confirmed working |  | Pass | Issue | P1 | PhilHealth deduction.mp4
The Payslip tab is only visible if the browser zoom or display setting is set to 100%. | Payslip tab.mp4 | Pending | Issue | P3 |  |  | For front end dev
Half day leave filed does not show half day in the portal | Half day leave.png | Pending | Issue | P2 |  |  | This is for front end, api is returning if it is half day
Payslip tab is not visible | UI | Pass | Issue | P3 | payslip video.mp4 | QA Comments: payslip is visible but need touchpad to swipe the tab bar |  | 2025-05-19
Mobile registration is not working in Apple | Registration in Apple.jpg | Pending | Issue | P1 | iOS login not working | stucked at loading after logging in with correct credentials | For mobile dev | 2025-05-19
Pop up error notif in setting up the company details | Pop up error.png | Pass | Issue | P3 | error pop-up.mp4 | No errors pop up |  | 2025-05-19
Half day work is presented as whole day work less half day undertime. This should be presented as half day work with no undertime |  | FOR QA | Issue | P2
Wrong Philhealth minimum amount. This should be P250 per month | PHIC min amount.png | Pass | Issue | P1 | philhealth.mp4 |  | This has been corrected, when salary is below 10000 , the philhealth amount is 250 per month | 2025-06-03
Important: Please add an adjustment field where all adjustments can be entered as a work around if an error in the calc arises or while you finalize some issues affecting the calculation | Adjustment field.png | Pending | Feature Request | P1
Details | Client Attachment | Status | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
Wrong SSS calculation | SSS Calc | Pass |  | wrong SSS calculation.mp4 | Wrong SS calculation and not accurate | Calculation should be correct , here's the table base on Ms Maydelyn testing
PHIC and HDMF minimum amount not set | PHIC and HDMF.png | Pass |  | the PHIC and HDMF is already set.mp4 | The PHIC and HDMF is need to setup in the MyOrganization tab
Allowance amount changed in the 2nd cutoff | Allowance | Pass |  | allowance in 2nd cutoff was not changed.mp4 | The Allowance amount was not changed in 2nd cutoff
Wrong undertime calc during special nonworking holiday | Undertime calc.png | Pass | P1 | no holiday.mp4 | There is no special holiday and regular holiday computation, but the system has the undertime computation | This has been fixed please retest | 2025-05-13
Half day leave/absent with undertime. Attached is a sample illustration for better understanding | Leave with late.png | Pass |  | No undertime deduction.mp4 Deduction.mp4
Unable to generate payslip for March 16-31 | Mar 31 payslip.mp4 | Pass |  | I can generate the payslip from march 16-31 2025.mp4 | Can generate payslip from March 16 to 31
Deleted public holidays still record and calculate as holidays in the payslip |  | Pending
Reset button for updating attendance is not working | Reset form button.mp4 | For Clarification | P3 | reset and update button.mp4 | reset button is working but cant save if you dont put data in time in and time out. But if you input the time it will be saved | Check with front end dev | May 05, 2025 cant save if you dont put data in time in and time out. But if you input the time it will be saved |  | Re
Wrong Net Pay calculation in payslip (SSS deduction is not considered) | Wrong total.png | Pass |  | wrong net pay calculation was fix.mp4 | SSS is already included in the deduction
Undertime was not taken into account when calculating SSS for the second cutoff | SSS calc for 2nd cutoff payslip | Pass |  | undertime was already taken.mp4 | Undertime is already taken when calculating SSS for the second cutoff
Please add the maximum and minimum contribution for Philhealth Minimum- P500.00 per month for salaries P10,000.00 and below. Maximum-2.5% of P100,000.00 (maximum salary) per month. | You may refer to this link. https://www.philhealth.gov.ph/advisories/2025/PA2025-0002.pdf | Pass |  | philhealth calc.mp4 | It doesn't add up the full contribution for PhilHealth it only adds up 1.8% | Maximum contribution already added, if salaray is greater than 100000 , contribution is 2500, which is 2.5% of 100000
Unable to generate payslip for February 16-28 cutoff | Payslip.mp4 | Pass |  | i can generate payslip for febraury 16-28.mp4 | February 16-28 can be generate
No year 2025 yet in the mobile app for leave tab | Earlee mobile.jpg | Pass |  | Year 2025 up is already available.jpg | There is no year 2025
Half day leave with late/undertime 1. If the half-day absence is filed as paid leave: |  | Pass |  | Still deducts.mp4 | It still deducts even though it is filed as leave
Half day leave with late/undertime 2. If the half-day absence is not filed as paid leave: |  | Pass |  | No undertime deduction.mp4 Deduction.mp4 | It deducts when it is not filed as leave
For new company registration, features not working: Bulk upload of employees | Bulk upload.mp4 | Pass |  | bulk upload employee now working.mp4 | bulk upload fixed | This has been retest , bulk upload is working please use the correct template. I sent it on the slack | June 10, 2025 Confirmed working
For new company registration, features not working: Manual registration of employees | Manual registration.mp4 | Pass |  | Can add members via manual reg.mp4 | It can register an employee via manual registration
Details | Client Attachment | Status | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
Upload company logo not working | Company logo.mp4 | Pass |  | (Working) Upload Profile.mp4 | Working |  |  |  | Acc used: Email: bryerallam@gmail.com Password: secretSecret1# Employee: Emily Sie Date Range: Month of Jan 2025
Wrong total in payslip (SSS deduction was not considered) | Wrong total.png | Pass | P1 | (Problem) Computation of Net Pay.mp4 | Problem: There is an extra 326.25 added to Net Pay - The 326.25 came from the SSS - On the client attachment it is the same that is why they have an extra 187.5
Undertime not considered in computing for SSS for 2nd cutoff | SSS calc for 2nd cutoff payslip | Pass | P1 | (Problem) Second Cutoff doesn't deduct UT.mp4 | Problem: The second cutoff doesn't deduct the UT that is why the SSS has increased price than expected
Please add the ceiling for Philhealth contribution This should be 2.5% of P100,000.00 (maximum salary) per month. You may refer to this link. | https://www.philhealth.gov.ph/advisories/2025/PA2025-0002.pdf | Pass |  | According to the table in the link, the income ceiling for PhilHealth contributions in 2025 is P100,000. This means that even if your salary is more than P100,000, your monthly premium will be capped at P5,000 (which is 5% of P100,000). You will not need to pay more than this amount, regardless of how high your salary is. | They want to add a ceiling in which no matter how high your salary is, you will still pay the 2.5% of 100,000 Example: If my salary is 150k i will only need to pay the 2.5% of 100k
Details | Client Attachment | Status | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes |  | Test account used: (Org not setup) vobarij605@maonyn.com secretSecret1#
Verification link sent to the email displays an error notification but the verification process pushed through | Org registration.mp4 | Pass | P2 | Wrong Page Showing Error Verifying even if it is Successful.mp4 | It is showing the wrong page, it should be a success page instead of Error
Unable to save the details entered in My Organization tab to set up company profile |  | Pass | P1 | Error setup organization.mp4 | There's an error on the setup of Organization. It won't submit even if all fields have values |  | (Fixed) My Org Won't Submit.mp4
Not working for bulk upload | Employee registration.mp4 | Pass |  | Working bulk register (Org Set Up).mp4 | The reason why they can't bulk register an employee is because the Organization is not yet set up Network Response: { "status": "error", "data": "Operation was not successful. Error: Error: No Data Available", "error": "Please create a company first" }
Not working for manual registration either |  | Pass |  | (Org not Set Up) Can't add employee issue.mp4 (Org Set Up) Can add employee.mp4 | The reason why they can't register an employee is because the Organization is not yet set up Network Response: { "status": "error", "data": "Operation was not successful. Error: Error: No Data Available", "error": "Please create a company first" }
Details | Client Attachment | Status | Priority | Checking Attachment | QA Remarks | Dev Remarks | Re-test Notes
For SSS calculation, the undertime hours were not considered in computing for the gross pay basis |  | Pass | P1 | UT SSS Issue.mp4 | - The current computation computes the whole Gross Pay, the case is it should be: (Gross Pay - UT) = What to compute for SSS Example: (12,000 - 500) = 11,500 11,500 will be the one that i will base for SSS instead of 12,000 |  | (Fixed) UT SSS Issue.mp4 |  | Acc used: Email: bryerallam@gmail.com Password: secretSecret1# Employee: Juan Dela Cruz Date Range: Month of Jan 2025 UT Date: Jan 14, 2025
For undertime calculation, 1 hour is being deducted. If an employee works from 9 AM to 5 PM, there should be a 1-hour UT/late deduction. However, the payslip does not show any UT/late. Same case if the employee works from 8AM to 3PM, there should be 2 hours UT but the payslip only shows 1hr UT. This is probably due to the adjustment made to consider the lunch break hour. https://drive.google.com/drive/folders/103LjioOSB9ZQD-BBwpd7F1FcbEWb4riI?usp=drive_link | 21 | Pass | P1 | No additional 1 hour issue PaySlip.mp4 | - The issue is that additional 1 hour deduction is removed due to recent changes on half day. - So any hour that i time out there will be no extra 1 hour added fo UT | For QA | (Fixed) UT No Additional 1 hour.mp4
Details | Status | Attachment | QA Remarks | Dev Remarks | Re-test Notes
sss 2025 has been update in DB - Check updated sss table : https://www.sss.gov.ph/wp-content/uploads/2024/12/2025-SSS-Contribution-Table-rev.pdf | Pass | (Updated) SSS Computation -.mp4
PHilhealth set to 2.50% and cannot be updated na (Kindly check if the philhealth declared on the org is still there and if yes, check the payslip if double yung PHIC. | Pass | (Updated) PhilHealth -.mp4 | ✔️ Philhealth working and added to My Organization -> Deductions ✔️ Philhealth cannot be edited and has fixed value ✔️ No duplication ✔️ Correct Computation
undertime lunch break not included (edited) | Pass | (Fixed) Undertime -.mp4
Login Verification not working | Pass | (Fixed) Employee Email Verification -.mp4 | ✔️ Updated verification link ✔️ Email for temp pass working ✔️ Working Employee Sign In
Details | Status | Client Attachment | Attachment | QA Remarks | Dev Remarks | Re-test Notes
Live link not working (Test was conducted using the link provided for testing) | Pass | Screenshot 2025-01-13 074827.png | (Fixed) Employee Email Verification.mp4 | Fixed |  | Fixed
Tried adding new employee but the email verification link sent to the employee's email did not work | Pass | Screenshot 2025-01-13 072639.png | (Fixed) Employee Email Verification.mp4 | Fixed |  | FIxed
Change password for mobile app is not working | Pass |  | Forgot Password on mobile not working Email Verification Link.webm | Email verification on forgot password not working - The site url still an OLD URL that is why it shows sites cannot be reached |  | Showing This site can’t be reached ✔️Tried on new email ✔️Tried on existing email
Log out button still not working | Pass |  | Mobile App Log Out Working.webm Web Admin Log Out Working.mp4 | Web Admin and Mobile Log Out working
The log-out button stops functioning if the site remains open for an extended period. | Pass |  | Fixed
The log-out button stops functioning after selecting a member on Teams -> Members -> Member | Pass |  | Fixed
SSS calculation is working however there is an updated SSS contribution guide released this January 2025. Please refer to this link for the updated SSS table https://www.sss.gov.ph/wp-content/uploads/2024/12/2025-SSS-Contribution-Table-rev.pdf | Pass |  | (Updated) SSS Computation.mp4 | Fixed |  | Fixed
PHIC should be autodeduct. This should be 2.50% of the basic pay per month | Pass |  | (Updated) PhilHealth -.mp4 | Fixed |  | Fixed
For undertime hours, if an employee works a half day (4 hours), the lunch break is included in the calculation. As a result, instead of 4 hours of undertime, it is calculated as 5 hours. | Pass |  | (Fixed) Undertime.mp4 | Fixed |  | Fixed
Details | Recording Attachment | Notes
Undertime | Undertime.mp4 | Employee Name: Juan Dela Cruz PayPeriod: Aug 1-15 2024 UT: August 14 8AM-1PM (4 hours UT)
Special Non Working Holiday (if employee works) - Premium calc in the payslip | Special Non Working Holiday showing prem calc.mp4 Special Holiday (Worked) Re-test Working.mp4 | Employee Name: Juan Dela Cruz PayPeriod: Sept 16-30 2024 Special Non Working Day: Sept 17, 2024
Half leave pay - It already direct reflect as leave in the payslip and not deducted in the standard pay calculation | Half leave pay already reflects.mp4 | Employee Name: Emily Sie PayPeriod: Aug 16-31 2024 Leave Requested: Aug 16, 2024
To Test | Issue | Client Attachment | Status | QA Testing Attachment | QA Remarks | Recheck Jan 2 | Status Jan 2 | Prod Status Jan 3^
SSS (Not SSS UT ONLY) | Undertime/late was not considered in the calculation |  | Checked | If only 1 hour UT the UT computation is not showing.mp4 | If UT is only 1 hour, the UT Computation is not showing, but if i got 2 hours and so on it works
PHIC | PHIC minimum contribution was not considered | PHIC Min.png | Checked | Philhealth 1.png | According to my research there is a minimum contribution (5% of an employees salary). https://www.philhealth.gov.ph/partners/employers/ContributionTable_v2.pdf The current system only supports: - Philhealth is not an automated but manually inputted on Deductions tab
Half leave pay | Half leave pay being deducted from the standard pay. It should direct reflect as leave in the payslip and not deducted in the standard pay calc | Half day leave.png | Checked, Fail | Half Leave pay deducts from standard pay.mp4 | The Half Leave Pay Deducts from standard pay | Already fixed: (Fixed)Leave Pay Deducts from Standard Pay.png | Pass | Pass
Undertime | If the employee works half day, the 1 hour lunch break is being included in the calculation of undertime (UT becomes 5hrs instead of just 4hrs) |  | Checked | No Minus 1 Hour if Half Day.mp4 | The 1 hour is being included on the undertime hours |  | Pass | Pass
Special Non Working Holiday (if employee works) | No premium calc in the payslip | SNWH 1.png SNWH 2.png SNWH 3.png | Checked, Fail | Special Holiday Not Working on PaySlip.mp4 | The Special Holiday + 30% is not added Note: This is an example with holiday pay Regular Holiday Pay.png | Special Holiday 30% not added.png | Pass | Pass
Regular Holiday | Regular Holiday (if employee does not work) final take is to be included in the STANDARD pay and not in the holiday pay. |  | Checked, Pass | Regular Holiday Working (Hindi Pumasok).mp4 | Pass It is already included on Standard Pay instead of Holiday Pay |  | Pass | Pass

## ADMIN TESTING
Column 1 | Importance | Issue Description | Attachment | QA Remarks | Jerome - Production | Joseph - Production | Louise - Production | Prod Status | Old LInk Status
Sign Up New Org |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Sign In |  |  |  |  | Pass | Pass | Pass
Account Verification | P3 | Button in the verification email not working, only the separated link is working |  |  | Pass | Pass | Pass
Forgot Password | P2 | Reset pass is working, however there's an misleading error message displaying | Reset pass issue.mp4 |  | Pass | Pass | Pass
Edit Org Details |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Viewing of Tax Rates (If has data) |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Adding Deductions | P1 | added deduction not displaying in the table | add deduction issue.webm |  | Fail | Fail | Fail | Pass | Pass
Editing Deductions | P2 | Edit deduction not working | edit deduction issue.mkv |  | Fail |  |  | Pass | Pass
Deleting Deduction | P2 | Deleting deduction not working | delete deduction issue.mkv |  | Fail
Adding Benefits and Allowance | P1 | Added Benefits and Allowance not Showing/Working | Add Benefits and Allowance Not Working (My Org Tab).mp4 |  | Fail | Fail | Fail | Fail | Fail
Adding Employee Documents |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Adding Public Holiday |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Payroll Settings - Company Shift |  |  |  |  | Pass | Pass | Pass | Pending | Pending
Payroll Settings - Total Working Days |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Payroll Settings - Leave Credits |  |  |  | Check if working ang company shifts (I think works for mobile? when someone timed in) | Pending | Pending |  | Pending | Pending
Add New Departments | P2 | Adding New Departments Not Working | Adding New Departments Not Working.mp4 |  | Fail | Fail | Fail | Fail | Fail
Update Time Logs (Attendance Tab) |  |  |  | December 23 Working: - Can Update and View Timelogs for specific day | Pass | Pass | Pass | Pass | Pass
Leave Request |  |  |  | December 23 Working: - Can Approve and Reject Leave Request | Pass | Pass | Pass | Pass | Pass
Change Shift | P2 | Change Shift Not Showing | Change Shift not Showing.png |  | Pending | Pending | Pending | Pending | Pending
Overtime |  | Rest Day Still Not Working |  | December 24 Working: OT Working and correct computation: - Ordinary - Special Holiday - Legal Holiday Not Working: - Rest Day | Pending | Pending | Pending | Pending | Pending
Payment Dispute Viewing | P1 | Requested Payment Dispute not Showing | Payment Dispute not showing.png |  | Pending | Pending | Pending | Pending | Pending
Ticket Request |  |  |  | December 23 Working: - Can Update Status, Ticket Type, Priority - Can View Images, Details etc. | Pass | Pass | Pass | Pass | Pass
Salary List Viewing | P3 | UI: Title is Leave Request instead of Salary List | Salary List Title.png |  | Fail | Pending | Fail | Fail | Fail
Click "Earlee" image in the sidebar | P2 | When clicked, redirecting into login page instead of dashboard | earlee image wrong page redirection.mp4 |  | Pending | Pending | Pending | Pending | Pending

## ADMIN EMPLOYEE TESTING
To Test | Importance | Issue Description | Attachment | QA Remarks | Jerome - Production | Joseph - Production | Louise - Production | Prod Status | Old Link Status
Add new Employee | P1 | Displaying: Error Verifying Account Instead of other page but the default password is working | Email Verification Unsuccessful.png (Mobile) Email Verification Unsuccessful |  | Pass | Pass | Pass | Pass | Pass
Edit Employee Details |  | Displaying error message and details are not saving | employee details not saving.mp4 |  | Pass | Pass | Pass | Pass | Pass
Add Employee Leave |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Edit Employee Leave |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Upload Document Button | P2 | Upload button not working | Upload Document button not working on Members Tab.mp4 |  | Fail | Fail | Fail | Fail | Fail
Add Employee Document |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Download Employee Document | P2 | Download button not Working | Download Employee Document Not Working.mp4 |  | Fail | Fail | Fail | Fail | Fail
Update Time Logs |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Add Deductions |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Edit/Delete Deductions |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Add Benefits |  |  |  | Known issue na yung nag duduplicate ung success | Pass | Pass | Pass | Pass | Pass
Edit/Delete Benefits |  |  |  |  | Pass | Pass | Pass | Pass | Pass
Generate PaySlip |  |  |  |  | Pass | Pass | Pass | Pass | Pass
PaySlip - Employee Info |  |  |  |  | Pass | Pass | Pass | Pass | Pass
(Daily) PaySlip - Earnings (Check all Computation) |  |  |  |  | Pass | Pass | Pass | Pass | Pass
(Daily) PaySlip - Deduction (Check all Computation) |  | Pending: Computation for Witholding Tax | If only 1 hour UT the UT computation is not showing.mp4 |  | Pending | Pending | Pending | Pending | Pending
(Daily) PaySlip - NetPay |  | Is NetPay: Gross Pay - Total Deductions? | Net Pay Wrong Calculation.png | [5 empty] | For Confirmation
(Fixed Month) PaySlip - Earnings (Check all Computation) |  |  |  |  | Pass | Pass | Pass | Pass | Pass
(Fixed Month) PaySlip - Deduction (Check all Computation) |  |  |  |  | Pending | Pending | Pending | Pending | Pending
(Fixed Month) PaySlip - NetPay |  | Is NetPay: Gross Pay - Total Deductions? | (Fixed Month) Net Pay Wrong Calculation.png | [5 empty] | For Confirmation
Check Special Holiday | P1 | Special Holiday computation not working | Special Holiday Not Working on PaySlip.mp4 |  | Pass | Pass | Pass | Pass | Fail
Check Regular Holiday |  |  | Regular Holiday Working (Hindi Pumasok).mp4 Regular Holiday Working (Pumasok).mp4.mp4 | As of December 19 the Regular Holiday "Pumasok" and "Hindi Pumasok" is working | Pass | Pass | Pass | Pass | Pass
Download Pay Slip |  |  |  | As of December 18 the Download Pay Slip is working Note: After downloading someting i need to refresh the page to download again | Pass | Pass | Pass | Pass | Pass
Close Button on Employee Side | P3 | Close Button is not working but the close icon is working. This applies to: (Members Tab) - Add Deduction and Edit Deduction Form - Add Benefits and Edit Benefits | Close Button Not Working.mp4 |  | Fail | Fail | Fail | Fail | Fail

## MOBILE TESTING
To Test | Platform | Issue Description | Attachment (Android) | Attachment | QA Comments | 1.2.4 (Prod) | Joseph - Prod (Android) | Louise - 1.2.4 (Prod) (Android) | Bry - 1.2.4 (Prod) (Android) | 1.1.1 (Prod) | Bry - 1.1.1 (Prod) (IOS) | Jerome - Prod (iOS)
Login | Both | When i logged in, it is only showing me a gray screen The site cannot be reached (Android) | Site can't be reached | (IOS) Can't continue to login | after logging in, stucked at gray screen | Pass | Fail | Pass | Pass | Fail | Fail | Fail
Forgot Password | Android | Forgot Password Not Working on Mobile App |  | (IOS) Email Verification Unsuccessful |  | Pass |  | Pass | Pass | Fail | Fail | Fail
My PaySlip | Android |  |  |  |  | Pass |  | Pass | Pass
Notifications | Android |  |  |  |  | Pending |  | Pass | Pending
Check-In | Android |  |  |  |  | Pass |  | Pass | Pass
Check-Out | Android |  |  |  |  | Pass |  | Pass | Pass
Add Posting (Newsfeed) | Android |  |  |  |  | Pass |  | Pass | Pass
Leave Request | Android |  |  |  |  | Pass |  | Pass | Pass
Overtime Request | Android |  |  |  |  | Pass |  | Pass | Pass
Ticket Request | Android |  |  |  |  | Pass |  | Pass | Pass
Shift Request | Android |  |  |  |  | Pass |  | Pass | Pass
Profile Dashboard | Android |  |  |  |  | Pending |  | Pass | Pending
Edit Profile | Android |  |  |  |  | Pass |  | Pass | Pass
Email verification | Android | No verification email has been sent to the email of the added employee |  |  |  | Fail

## MOBILE SCENARIOS
Scenario | Platform | Issue Description | Attachment | QA Comments | 1.2.4 (Prod) | Bry - 1.2.4 (Prod) | Louise - 1.2.4 (Prod) | Joseph - 1.2.4 (Prod) | 1.1.1 (Prod)
Check-out under half day | Android |  |  |  | Pass | Pass | Pass
Add Empty task validation | Android |  |  |  | Pass | Pass | Pass
Post Empty Caption and Photo | Android |  |  |  | Pass | Pass | Pass
Selecting 0 Balance Leave Type | Android |  |  |  | Pass | Pass | Pass
Creating Leave Request Without: - Schedule - Day - Reason | Android |  |  |  | Pass | Pass | Pass
Requesting Overtime without Checking out | Android |  |  |  | Pass | Pass | Pass
Creating Ticket Without: - Issue - Ticket type | Android |  |  |  | Pass | Pass | Pass
Creating Shift Request Without: - Reason - Date - Start/End | Android |  |  |  | Pass | Pass | Pass
Submitting Payment Dispute Without Description | Android | The Payment Dispute is not pushing through but it is showing Payment Dispute has been sent And Payment Dispute no validation on details text field | Payment Dispute No Details Not Pushing Through but Showing Payment Dispute has been sent.webm |  | Pass | Pass | Pass

## ADMIN SCENARIOS
Scenario | Module | Issue Description | Attachment | QA Comments | Prod Status | Bry - Prod Status | Louise - Prod Status | Joseph - Prod Status | Jerome - Prod Status | Old Link Status
Saving Employee Details Without All Required Field - Basic Info - Compensation - Govt Agency Details - Work History - Bank Info - Emergency Contact | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Saving Leave Options Without: -Type - Num of Leave - Balance | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Adding Documents Without an Attachment | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Updating Time Logs Without: - Date range - Time In & Out - Reason | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Adding Deductions Without: - Description - Rate - Rate Type | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Adding Benefits Without: - Description - Rate - Rate Type | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Generate PaySlip Without: - Payroll Period - Paydate | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Add Deductions Without: - Description - Rate = 0 | My Organization | Can click save without adding description | Can click submit without description (Deductions).mp4 |  | Fail | Fail | Fail | Fail | Fail | Fail
Add Benefits Without: - Description - Rate = 0 | My Organization |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending
Add Employee Documents Without: - Title | My Organization | Can click save without adding Title | Can click save without title (Employee Doc).mp4 |  | Fail | Fail | Fail | Fail | Fail | Fail
Add Public Holiday Without: - Title - Rate - Date | My Organization | Can click save without adding required fields | Can click save without required fields (Holiday).mp4 |  | Fail | Fail | Fail | Fail | Fail | Fail
Add New Department Without: - Title - Head - Members | Departments |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending
Update Time Logs Without: - Employee - Date Range - Time in & out - Reason | Attendance |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Leaves - Reject | Leaves |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Change Shift | Change Shift |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending
Overtime | Overtime |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending
Payment Dispute | Payment Dispute |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending
Ticket Request - Save note without text - Update diff combination | Ticket Request |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Update Time Logs By Typing in the time | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Update a Time Log By Typing in the time | Teams/Members |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Update a Time Log By Typing in the time | Attendance |  |  |  | Pass | Pass | Pass | Pass | Pass | Pass
Once a half-day leave has been filed for a half-day absence, any late by the employee is not counted in the UT. | Payslip | Late is still counted in the UT even if half-day leave has filed | Half-day UT computation in filed half-day leave issue.mp4 |  | Fail