## DEV FIX URGENT
List of items based on Priority for Fixing and implementation
Details | Status | Fix Percentage | Remarks | QA Status | Dev Remarks
1. No analysis on frameworks listed | Fail | 95% | Click Here (No Analysis Table)
2. Manual import result for the chowking survey result | Done | 100% | two survey name: "Chowking Vow to Wow T3" and "Vow to WOW!". |  | Need access ng db to ate aryhan, need copy ng version of env.
3. When a user provides a long answer in the download report analysis, the response is cut off in the PDF. | Done | 100% | Suggestion : To limit the input answer Sample PDF: https://drive.google.com/file/d/13uHM6fy-67vXNYilJqDxTF2iluOgapUr/view?usp=sharing |  | Done Fix 7/15
4. Fix Create Survey from Scratch not working | Done | 95% | Click here (Survey from Scratch Table) | Pending | Analyze Generate (AI) is not working
5. Fix Ading new forms on Frameworks | Pass | 100% | Click here (Adding forms per Framework Table)
6. Fix other remaining issues | Fail | 80% | Click here (Other Frameworks issue \Table) | Pending | Some interpretations are not appearing and some are fixed already
7. Upcoming manual imports for the survey results
8. Payment Integration Feature | In Progress |  | Kindly input here the estimates sir aeverano63@gmail.com: 3 months estimate 2 months for development and 1 month for testing |  | By october PAyment Integration will be finished
8.1 Payment UI | To-do
8.2 Payment Function | To-do
9. Email summary and list of my responses if im a respondent and left my email or a registered user | To-do
10. Ability of admin to view list of respondents then click a respondent and have a dashboard of the persons responses | To-do
11. Create a summary and analysis of that persons responses | To-do
12. . history of response and ability to compare and contrast my responses and results | To-do
13. Make kendra icon Bigger | Done
14. Add an effect or textbox on beside kendra "Want me to analyze your data?" | Done
15. For one Company admin account, the system can have the ability to add multiple admins. | To-do
16. New Framework - 30-Day Post-Training Learning Impact Survey.xlsx | Done |  | Framework - https://docs.google.com/spreadsheets/d/1LAIGDA_1F6PQhxc-_m9qz_qsjGA00F8u/edit?usp=sharing&ouid=105953030057432847482&rtpof=true&sd=true
17. New last question in Post WOrkshop Survey: "Please leave a one-liner about the session we had with you." Long Answer | Done
18: IMPAK FRAMEWORK 16: Pre Training Baseline | Done

## PRIORITY ITEMS FOR FIXING
Framework | Status | Issue Details | Attachment | QA Comments | Dev Comments | Last Re-test
Onboarding | Done |  |  |  |  | 2025-06-16
NPS | Done | Kendra analysis not working properly | NPS_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Org Analysis | Done |  |  |  |  | 2025-06-16
Program Reaction | Done | Kendra analysis not working properly | ProgramReaction_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Program Assimilation | Done | Kendra analysis not working properly | ProgramAssimilation_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Learning Impact | Done |  |  |  |  | 2025-06-16
Moodwave | Done | Kendra analysis not working properly | Moodwave_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Optimism | Done | Kendra analysis not working properly | Optimism_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Adult Hope | Done | Kendra analysis not working properly | AdultHope_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Org Culture | Done | Kendra analysis not working properly | OrgCulture_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Learning Organization | Done | Kendra analysis not working properly | LearningOrg_NoKendraAnalysis.mp4 |  |  | 2025-06-16
Change Management | Done | Kendra analysis not working properly | ChangeManagement_NoKendraAnalysis.mp4 |  |  | 2025-06-16
STAY Exit Survey | Done | Kendra analysis not working properly | StayExit_NoKendraAnalysis.mp4 |  |  | 2025-06-16
There are inconsistencies within each kendra analysis. Some surveys are analyzed, some are not. Under investigation
To Test | Status | Priority | Platform | Public or Private | Issue Details | Web Attachment | Mobile Attachment | QA Comments | Dev Comments | Last Re-test
Onboarding | Pass |  | Website | Public | [5 empty] | 2025-03-28
NPS | Pass |  | Website | Public | [5 empty] | 2025-03-28
Org Analysis | Pass |  | Website | Public | [5 empty] | 2025-03-28
Program Reaction | Pass |  | Website | Public | [5 empty] | 2025-03-28
Program Assimilation | Pass |  | Website | Public | [5 empty] | 2025-03-28
Learning Impact | Pass |  | Website | Public | [5 empty] | 2025-03-28
Moodwave | Pass |  | Website | Public | [5 empty] | 2025-03-28
Optimism | Pass |  | Website | Public | [5 empty] | 2025-03-28
Adult Hope | Pass |  | Website | Public | [5 empty] | 2025-03-28
Org Culture | Pass |  | Website | Public | [5 empty] | 2025-03-28
Learning Organization | Pass |  | Website | Public | [5 empty] | 2025-03-28
Change Management | Pass |  | Website | Public | [5 empty] | 2025-03-28
STAY Exit Survey | Pass |  | Website | Public | [5 empty] | 2025-03-28
To Test | Status | Priority | Issue Details | Attachment | QA Comments | Dev Comments | Last Re-test
Create Public Survey | Pass | [5 empty] | 2025-03-28
Create Private Survey | Pass | [5 empty] | 2025-03-28
Analyze Generate (AI) | Pass | P3 | Theres an error pop up says "Rationale field must have at least 15 characters" even though already entered more than 15 characters | Analyze and Generate error.mp4 |  | Fixes the rationale issues but analyze generate AI still isnt working on live. Must be queuing issues because I can run it locally | 2025-06-25
Check Survey Link | Pass | [5 empty] | 2025-03-28
Check if Added Short Answer, Long Answer etc. is working | Pass | [5 empty] | 2025-03-28
Add Short Answer | Pass | [5 empty] | 2025-03-28
Add Long Answer | Pass | [5 empty] | 2025-03-28
Add Date | Pass | [5 empty] | 2025-03-28
Add Time | Pass | [5 empty] | 2025-03-28
Add Checkbox | Pass | [5 empty] | 2025-03-28
Add Radio Button | Pass | [5 empty] | 2025-03-28
Add Range Slider | Pass | [5 empty] | 2025-03-28
Add Section | Pass | [5 empty] | 2025-03-28
2025-03-28
2025-03-28
2025-03-28
2025-03-28
To Test | Status | Issue Details | Attachment | QA Comments | Dev Comments | Re-test Attachment | Last Re-test
Share link on the same page after creating a Survey | Done | Can't click share button after creating new Survey. | Can't Click Share Public Link.mp4 | Fixed as of June 10, 2025 |  | Share link on the same page after creating a Survey(FIXED)).mp4 | 2025-06-10
Forms date and time | Done
Long Answer on PDF Export | Done | When a framework result is exported, long answers overflow. |  |  |  | VibeCheckPublic06242025.pdf | 2025-06-25
Survey Analytics PDF Export | Done | Cant export a pdf or waiting time too long | pdf export not working | Fixed as of June 10, 2025 |  | Survey Analytics PDF Export(FIXED).mp4 | 2025-06-10
Generate Survey From Scratch | Done | No survey questionnaire created after filling out the setup form and clicked analyze and generate | AI from scratch.webm | I waited for almost 15 minutes but no survey questionnaire was generated | It works but refreshing is needed which is counter to what I would want to happen. Thinking of better solutions that may not require events in general |  | 2025-06-25

## Impak App Client Feedback as of
Framework | Status | Device Used | Priority | Issue Details | Attachment | QA Comments | Dev Comments | Last Re-test
Learning Impact Survey Navigation Issue The user had to click the Next button several times before it would respond and move to the next page. | Pass | Android |  |  | Navigation.mp4 | The user can easily navigate through the next question
Onboarding Experience Survey Lack of Per-Question Back Button There is no back button available on each individual question. | Fail | Android | Priority 1 | There is no back button while taking the survey | Back button.mp4
Onboarding Experience Survey Suggestion for Page Consolidation Would it be possible to have all the ratings for each category on a single page? There are 33 pages, and some people might think it will take a long time to complete and decide not to answer. If it's consolidated per category, the progress bar would show fewer pages. Categories: Culture, Compliance, Connection, Clarifications, Open Ended Question Eg. Counting of question will be per category (Culture 1 of 5) If not, are there any other options? | To-do | Laptop | Priority 1 | Feature request by the client
Onboarding Experience Survey Page Reset after Interruption When I exited in the middle of responding, when I went back, it goes back to the beginning page again | Pass | Any Device |  | The page doesn't go back after being reset | Page reset after interuption.mp4
Onboarding Experience Survey Suggestion for Clarity After Reminders After the reminders, it would be helpful to include instructions to move the cursor to select a level from 1 to 5. | To-do | Any Device | Priority 1 | Feature request by the client
MoodWave: Empoyee Vibe Check Lack of Per-Question Back Button There is no back button available on each individual question. | Fail | Any Device | Priority 1 | There is no back button | MoodWave no back button.mp4
Optimism Survey Lack of Per-Question Back Button There is no back button available on each individual question. | Fail | Android | Priority 1 | There is no back button | Optimism no back button.mp4

## Summary Results
Framework Name | Requirement File | Info | Type | Platform | Survey | Status | Issue Details | Attachment | Dev remarks/question | Version When Re-Tested | QA Test Attachment | QA Status
Organizational Culture | ORGANIZATIONAL CULTURE ASSESSMENT_draft.docx | Randomized Questionnaire | Feature Request | Web, Mobile | Public and Private | Done | Items per question is not randomized (Based on the Client Concern: Consider randomizing items per question) |  |  |  |  | Passed
NPS |  | Rating Scale on Question 1 (If answer 9 or 10) | UI | Mobile | Public and Private | Done | Rating or Mood Scale instead of multiple choice | Rating scale instead of multiple choice |  | Version 1.1.1 | Still a mood or rating scale.png | Passed
Simple Org Analysis | Framework 8_Simple Org Needs Analysis_Final.docx | Summary Analysis | Feature Request | Web |  | Done | There is no Summary Analysis | Missing Summary Analysis.png Scoring: Simple Org Analysis Scoring.png |  |  |  | Passed
The Learning Organization | THE LEARNING ORGANIZATION SURVEY_draft.docx | Answers Record Save When Going Back | Bug Report | Mobile | Public and Private | Done | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working |  | Version 1.1.1 | Fixed Continue Button (The Learning Org) | Passed
The Learning Organization |  | Instructions in welcome page | UI | Mobile | Public and Private | Done | No instructions in the respondent welcome page when starting a survey | No Instructions in Welcome Page.jpg |  | Version 1.1.1 | Instructions done.png | Passed
The Learning Organization |  | Total Score | Bug Report | Web |  | Done | Analyze yielded Score of 0 (Score not updating only 0) | The Learning Organization Zero Score Issue.png | removed score 0, because every section has its own score computation |  |  | Passed
The Learning Organization |  | Summary | Bug Report | Web |  | Done | Shared Vision and Team Learning has swapped text on Score 6 below | Issue: Shared Vision and Team Learning swapped text.png |  |  | Solved Swapped Text.png | Passed
The Learning Organization |  | Average Score in Summary | Bug Report | Web |  | Done | Score not updating and is only basing on the first survey answered | Score on summary not updating.mp4 |  |  | Fixed Score Stucked on first survey response.mp4 | Passed
Change Management Effectiveness | CHANGE MANAGEMENT EFFECTIVENESS CHECK_draft.docx | Answers Record Save When Going Back | Bug Report | Mobile | Public and Private | Done | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working |  | Version 1.1.1 | Fixed Continue Button (Change Management) | Passed
Change Management Effectiveness |  | Instructions in welcome page | UI | Mobile | Public and Private | Done | No instructions in the respondent welcome page when starting a survey | No instructions in Welcome Page |  | Version 1.1.1 | Instructions done.png | Passed
Change Management Effectiveness |  | Total Score | Bug Report | Web |  | Done | Score not updating only 0 | Score just a static 0.png | removed score 0, because every section has its own score computation |  |  | Passed
Change Management Effectiveness |  | Average Score in Summary | Bug Report | Web |  | Done | Average Score not updating (stucked on the average score of first answered survey) | Average Score not updating.mp4 |  |  | Fixed Score Stucked on first survey response.mp4 | Passed
Stay Exit Survey Test | THE STAY EXIT SURVEY.docx | Sequenced Questionnaire | Bug Report | Mobile | Public and Private | Done | Started with open-ended right away, and questions are shuffled per section instead of sequenced like in the requirement file | Questionnaire not properly sequenced |  | Version 1.1.1 | Not sequenced (Hindi magkakasunod).webm The questions are still randomized instead of sequenced(magkakasunod). Requirement screenshot: (Applicable to all not just the first part) Sequenced requirements.png The web is already on sequence. The mobile version questions is still randomized. | Passed
Stay Exit Survey Test |  | Answers Record Save When Going Back | Bug Report | Mobile | Public and Private | Done | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working |  | Version 1.1.1 | Fixed Continue Button (Stay Exit).webm | Passed
Stay Exit Survey Test |  | Instructions in welcome page | UI | Mobile | Public and Private | Done | No instructions in the respondent welcome page when starting a survey | No instructions in welcome page |  | Version 1.1.1 | Instructions done.png | Passed
Stay Exit Survey Test |  | Summary | Bug Report | Web |  | Done | No summary showing and there is no Analysis/Summary Button | No Summary and Analysis.png | in documentation, it doesn't specify how to compute score |  |  | Passed

## Post Event Measuring the Basi
To Test | Status | Priority | Platform | Public or Private | Issue Details | Web Attachment | Mobile Attachment | QA Comments | Dev Comments | Last Re-test
Post Workshop | Fail | P1 | Both | Public | Time Field: - Can't proceed because it requires time field (Website) Date Field: - Can't proceed because it requires date field (Website) Radio Button: - No option to add choices if you clear all choices CheckBox: - No option to add choices if you clear all choices Text Preview: - When adding a custom question there is no Preview of the title - Add custom question -> No Default Preview -> Add Title -> No Preview | Time Field: Post Workshop No Time.mp4 Date Field: Post Workshop No Date.mp4 | Time Field: https://drive.google.com/file/d/11Q7ST5ohwQ2kt_5hvDeu4UD2zLmaNxML/view?usp=drive_link Date Field: https://drive.google.com/file/d/11OD-B8spH9xEntgC40LaOPFvUYTmsRej/view?usp=drive_link |  |  | 2025-04-03
Post Events | Fail | P1 | Both | Public | Time Field: - Can't proceed because it requires time field (Android) - In time section, it appears to be wrong (Website) Date Field: - Can't proceed because it requires date field (Website & Android) | Time Field: Post Event Time section is wrong.mp4 Date Field: Post Event No Date.mp4 | Time Field: https://drive.google.com/file/d/11VA7brYE29dmHy8Jp2zBNzbhlBvPznni/view?usp=drive_link Date Field: https://drive.google.com/file/d/11VA7brYE29dmHy8Jp2zBNzbhlBvPznni/view?usp=drive_link |  |  | 2025-04-03

## ORGANIZATIONAL CULTURE Test
To Test | Platform | Private Survey | Public Survey | Issue Details | Attachment
Randomized Questionnaire | Web | NP | NP | Items per question is not randomized (Based on the Client Concern: Consider randomizing items per question) | NP | Yellow means from Client Comment
Dimension 1 (Scoring) | Web | Pass | Pass
Dimension 2 (Scoring) | Web | Pass | Pass
Dimension 3 (Scoring) | Web | Pass | Pass
Dimension 4 (Scoring) | Web | Pass | Pass
Dimension 5 (Scoring) | Web | Pass | Pass
Dimension 6 (Scoring) | Web | Pass | Pass
Randomized Questionnaire | Mobile | NP | NP | Items per question is not randomized (Based on the Client Concern: Consider randomizing items per question) | NP
Dimension 1 (Scoring) | Mobile | Pass | Pass
Dimension 2 (Scoring) | Mobile | Pass | Pass
Dimension 3 (Scoring) | Mobile | Pass | Pass
Dimension 4 (Scoring) | Mobile | Pass | Pass
Dimension 5 (Scoring) | Mobile | Pass | Pass
Dimension 6 (Scoring) | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working.mov
Analysis has NOW vs PREFERRED, but this was not reflected in the questionnaire | Web | Pass | Pass | There is already NOW and PREFERRED on the Summary | Now VS Preferred.png

## NPS Test
To Test | Platform | Private Survey | Public Survey | Issue Details | Attachments
For Promoters (answered 9 or 10 on question 1) | Web | Pass | Pass
For Passives (answered 7 or 8 on question 1) | Web | Pass | Pass
For Detractors (answered below 7) | Web | Pass | Pass
Summary | Web | Pass | Pass
Others, please specify option | Web | Pass | Pass | Note: On the link sharing option "Other, please specify" option is Working, only the Web app is not working. The "Others, please specify" is a selectable button instead of a textfield | NPS Testing Others, please specify is not a textfield (All Questions with Others option).png
For Promoters (answered 9 or 10 on question 1) | Mobile | Pass | Pass
For Passives (answered 7 or 8 on question 1) | Mobile | Pass | Pass
For Detractors (answered below 7) | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass

## CHANGE MANAGEMENT EFFECTIVENESS
To Test | Platform | Private Survey | Public Survey | Issue Description | Attachment
Randomized Questionnaire | Web | Pass | Pass |  |  | Yellow means from Client Comment
Checking Questionnaire | Web | Pass | Pass
Randomized Questionnaire | Mobile | Pass | Pass
Checking Questionnaire | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working
Instructions in welcome page | Mobile | Pass | Pass | No instructions in the respondent welcome page when starting a survey | No instructions in Welcome Page Requirement File: CHANGE MANAGEMENT EFFECTIVENESS CHECK_draft.docx
Analysis Score | Web | Pass | Pass | Score is 0 in analysis
Total Score | Web | Pass | Pass | Score not updating only 0 | Score just a static 0.png
Summary | Web | Pass | Pass | Client Comment: Summary needs to be clearer | The summary is based on the requirements
Data cuts | Web | Pass | Pass | Data cuts seems to be missing | Requirement File: CHANGE MANAGEMENT EFFECTIVENESS CHECK_draft.docx
Average Score in Summary | Web | Pass | Pass | Average Score not updating (stucked on the average score of first answered survey) | Average Score not updating.mp4

## THE LEARNING ORGANIZATION Test
To Test | Platform | Private Survey | Public Survey | Issue Description | Attachment
Randomized Questionnaire | Web | Pass | Pass |  |  | Yellow means from Client Comment
Checking Questionnaire | Web | Pass | Pass
Randomized Questionnaire | Mobile | Pass | Pass
Checking Questionnaire | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working
Instructions in welcome page | Mobile | Pass | Pass | No instructions in the respondent welcome page when starting a survey | No Instructions in Welcome Page.jpg
Analyze yielded Score | Web | Pass | Pass | Analyze yielded Score of 0 | The Learning Organization Zero Score Issue.png
Summary | Web | Pass | Pass | Shared Vision and Team Learning has swapped text on Score 6 below | Issue: Shared Vision and Team Learning swapped text.png Requirement File: THE LEARNING ORGANIZATION SURVEY_draft.docx
Average Score in Summary | Web | Pass | Pass | Score not updating and is only basing on the first survey answered | Score on summary not updating.mp4
Analysis | Web | Pass | Pass | Loading times (limited by plan) | If tab is what client is looking for: Analysis Existing.png

## STAY EXIT SURVEY Test
stay | Platform | Private Survey | Public Survey | Issue Description | Attachment
Sequenced Questionnaire | Web | Pass | Pass |  |  | Yellow means from Client Comment
Checking Questionnaire | Web | Pass | Pass
Sequenced Questionnaire | Mobile | Pass | Pass | Started with open-ended right away, and questions are shuffled per section instead of sequenced like in the requirement file | Questionnaire not properly sequenced Requirement File: THE STAY EXIT SURVEY.docx
Checking Questionnaire | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass | When i clicked the back button while on the survey question and start the survey again, it does not allow me to continue | Continue button not working
Instructions in welcome page | Mobile | Pass | Pass | No instructions in the respondent welcome page when starting a survey | No instructions in welcome page Requirement File: THE STAY EXIT SURVEY.docx
Total Score | Web | Pass | Pass
Summary | Web | Fail | Fail | No summary showing and there is no Analysis/Summary Button | No Summary and Analysis.png

## SIMPLE ORG ANALYSIS Test
To Test | Platform | Private Survey | Public Survey | Issue Description | Attachment
Checking Questionnaire | Web | Pass | Pass |  |  | Yellow means from Client Comment
Instructions in welcome page | Mobile | Pass | Pass
Checking Questionnaire | Mobile | Pass | Pass
Answers Record Save When Going Back | Mobile | Pass | Pass
Summary Analysis | Web | Pass | Pass | There is no Summary Analysis | Missing Summary and Analysis.png
Back Button | Mobile | Pass | Pass | There is a working back button | Back button existing
Score is 0 in analysis | Web | Pass | Pass | There is a score in analysis | Score in Analysis.png
1 Open-ended question appeared early | Web | Pass | Pass | There is no Open-ended question appeared early, it might be the question from Part 1 in the requirements
1 Open-ended question appeared early | Mobile | Pass | Pass
Description

## (MOBILE) Sign Up
To Test | Platform | Version When Tested | Status | Issue Description | Attachment
Forgot Password | IOS | Version 1.1.2 | Pass |  | Retested: Dec 16 (IOS) Forgot Password
Forgot Password | Android | Version 1.1.1 | Pass |  | Retested: Dec 16 (Android) Forgot Password
Change Password | Android | Verson 1.1.4 | Pass
Change Password | IOS | Version 1.1.2 | Pass