## (Mobile) Suggestions
Topic | Tester Name | Details/Notes | Attachments
Bottom Navigation Bar Adjustment - TIDEE CUSTOMER | Jerome - QA Intern | Suggestion to adjust the position of the bottom nav bar because its overlapping with the horizontal line of IOS at the bottom | bottom nav.jpg
Mobile number must also have a verification process - TIDEE CUSTOMER | Bryan | The current app only supports email verification
Add update function on Address - TIDEE Cleaner | Ced | Currently disabled, need to implement for future release
Add editing option for Cleaner Profile | Bryan | Currently disabled, need to implement for future release | (IOS) Edit option removed.png

## (Web) Suggestions
Topic | Tester Name | Details/Notes | Attachments

## SUMMARY RESULTS
Details | Info | Priority | Type | Platform | Date Tested | Version When Tested | Status | Issue Description | Attachment | Dev remarks/question | QA Checking Attachment | QA Status
TIDEE Cleaner | Cleaner reject job | P1 | UI | IOS | April 7, 2025 | 1.0.2 production | Failed | Wrong text on rejecting booking confirmation dialog: - No keep it -> Yes - Yes, Cancel -> No Baliktad yung text sa confirmation button | (IOS) Wrong booking cancellation confirmation dialog.mp4 |  | Waiting for IOS Deployment (Android) (Fixed) Pop-up Text.jpg | Failed
TIDEE Customer | Deleting Address | P2 | Bug Report | IOS, Android | April 7, 2026 | 1.0.0 (12) |  | Delete action not working | (IOS) Delete address not working.mp4 Delete address not working.mp4
TIDEE Customer | Editing Address | P2 | Bug Report | IOS, Android | April 7, 2027 | 1.0.0 (12) |  | Edit button not working | (IOS) Edit Address not working.mp4 Edit button not working.mp4
TIDEE ADMIN | Assigning of Cleaner | P1 | Bug Report | Web Admin | April 7, 2025 |  | To-do | Cant add new cleaner and cant assign cleaner because there is no available cleaner on the Cleaners overview | Cant add new cleaner.mp4 |  |  | Failed
TIDEE Cleaner | ⁠Cleaner app see job assigned | P1 | Bug Report | IOS | April 7, 2029 | 1.0.0 (10) | Done | Viewing Pending and Assigned showing Error/Gray Container | (IOS) Viewing Jobs Issue.mp4 |  | (IOS) Fixed Viewing Job Issue.mp4 | Passed
TIDEE Cleaner |  |  |  |  | April 7, 2030 | 1.0.0 (10)
TIDEE ADMIN | Cleaners Overview | P1 | Bug Report | Web Admin | April 7, 2025 |  | To-do | No cleaner available in cleaners overview | No cleaner available.mp4 |  |  | Failed
TIDEE Cleaner | Cleaner Add Availability | P1 | Bug Report | Android | April 7, 2025 | 1.0.2 production | Done | There is no Add Option Compared to IOS UI | (IOS) Availability UI (Android) No Plus Icon Availability.jpg |  |  | Passed
TIDEE ADMIN | ⁠Admin assign cleaner through order details | P1 | Bug Report | Web Admin | April 7, 2025 |  |  | Assigning through order details not working and details of assigned cleaner is blank. | Assigning through order details not working.mp4 |  |  | Passed
TIDEE Cleaner | Adding Availability | P2 | UI | IOS, Android | April 7, 2025 | 1.0.2 production | Done | Different UI regarding Adding Availability Android: - With Multiple Selectable Button on Top | (IOS) Availability UI (Android) Availability UI.jpg |  |  | Passed
TIDEE Cleaner | Update profile as user | P2 | Bug Report | IOS, Android | April 7, 2035 | 1.0.0 (11) |  | The Gender and BirthDate input during creation of account is not saved as default on the Profile information, | Date of birth and gender as default issue.jpg (IOS) Gender and Bday inputted during creation not displaying.jpg
TIDEE Cleaner | ⁠Cleaner see accepted job on schedule | P1 | Bug Report | IOS | April 7, 2036 | 1.0.0 (9) | Done | Time not in the right format | (IOS) Wrong time text format.jpg |  | (IOS) Fixed time format.jpg | Passed
TIDEE Cleaner | Update profile as user | P2 | Bug Report | IOS | April 7, 2037 | 1.0.0 (11) |  | Mobile number created from Create Profile not saved | (IOS) Contact number inputted during creation not displaying.jpg
TIDEE Customer | Deleting and Editing Address | P2 | UI | IOS | April 7, 2038 | 1.0.0 (14) | Done | No Editing and Deleting Button | (IOS) No edit and delete.jpg |  |  | Passed
TIDEE Cleaner | navigating to my availability page bug | P2 | Bug Report | IOS | April 7, 2039 | 1.0.0 production and 1.0.0 (12) | For QA | "My availability" page not loading, need to change page then go back to "my availability" page to display the list | my availability issue.mp4 |  |  | Passed
TIDEE Cleaner | Update profile as user | P2 | Bug Report | IOS, Android | April 7, 2025 | 1.0.2 production | Failed | No edit button for editing profile deatils (Android) Cannot Update Profile Information | No edit button.mp4 (IOS) Unable to update overall profile.mp4 |  |  | Failed
TIDEE Cleaner | Update profile as user | P2 | Bug Report | IOS, Android | April 7, 2025 | 1.0.2 production | Failed | The profile picture is not displaying in the Profile Information section. | Profile pic not on profile info.mp4 (IOS) Unable to update profile picture.mp4 |  |  | Failed
TIDEE Customer | Customer Booking Summary | P2 | UI | IOS | April 7, 2025 | 1.0.2 production | Failed | Wrong booking time text format | (IOS) Time format issue on booking.jpg |  | IOS wrong time format | Failed
TIDEE ADMIN | Assigning Cleaner | P2 | Feature Request | Web Admin | April 7, 2025 |  | Done | Scroll not working/Overflow if displaying 20+ above when assigning a job to a cleaner Job Orders List -> Selecting a Job -> Clicking Edit Icon(Assigning) -> Expanding the interface to 20 to view all cleaner -> Can't Scroll | (Admin) See Available Cleaners Not Scrollable.mp4 |  |  | Passed
TIDEE Customer | Allow the user to input zero at the beginning in mobile number field | P3 | Bug Report | IOS, Android | April 7, 2025 | 1.0.2 production | In progress | The app allows inputting a 0 at the beginning, but when saved, the 0 disappears. | (IOS)0 on front mobile number issue putting 0 on front mobile number issue.mp4 |  | Zero in the beginning still not included upon saving | Failed
TIDEE Customer | Forgot Password | P3 | Feature Request | IOS, Android | April 7, 2025 | 1.0.2 production | Failed | Reset password email not sending to the email provided | forgot pass not sending email.MP4 No email for change pass.mp4 |  | https://drive.google.com/file/d/1xK_ekaOnNjUzhWfloUcFKP5o067cSGfL/view?usp=drivesdk | Failed
TIDEE Customer | Phone number country code | P3 | Bug Report | IOS, Android | April 7, 2025 | 1.0.2 production | In progress | Phone number country code not saving | (IOS) Phone number country code not saving.mp4 Phone country code not saving.mp4 |  | https://drive.google.com/file/d/1l9oxykZAi3DiZ-1JOoThgkmZXrXdodCn/view?usp=drivesdk | Failed

## WEB ADMIN
To Test | Platform | Issue Description | Attachment | Status | Bry - Status | Joseph - Status | Jerome - Status | Louise - Status | QA Comments
Admin web signup | Web
Admin web app log in | Web |  |  | Pass | Pass | Pass | Pass | Pass
Admin web forgot password | Web |  |  | Pending | Pending
Admin see order on orders list | Web |  |  | Pass | Pass | Pass | Pass | Pass
Admin see order details | Web |  |  | Pass | Pass | Pass | Pass | Pass
⁠Admin assign cleaner through action buttons | Web |  |  | Pass | Pass | Pass | Pass | Pass
⁠Admin assign cleaner through order details | Web | Assigning through order details not working and details of assigned cleaner is blank. | Assigning through order details not working.mp4 | Fail | Pass | Pass | Pass | Pass
Admin web app see order status update | Web |  |  | Pass | Pass | Pass | Pass | Pass
Admin assign cleaner when Available | Web |  |  | Pass | Pass | Pass | Pass | Pass
Admin assign cleaner when not Available | Web | Can Assign even if the cleaner is not available | (Admin) Can Assign even if cleaner not available.mp4 | Fail | Fail | Fail | Fail | Fail
Admin see cleaner details | Web | Blank page only | No Cleaners OverView.webm | Fail | Fail | Fail | Fail | Fail

## CLIENT REPORTS
Details | Status | Platform | Android Attachment | IOS Attachment | Android Version | IOS Version | QA Remarks | Dev Remarks | Notes
Change "Tidy" to TIDEE | Pass | Both | No issue detected No Tidy text anymore.jpg | No issue detected |  | 1.0.0 (12) | Fixed (Just a text data from database)
Misplaced booking time | Pass | IOS | No issue detected | (IOS) No misplaced time 1 (IOS) No misplaced time 2 |  | 1.0.0 (12) | No issue detected
Bug in country code selection when selected a country, user will be redirected to the homepage | Pass | IOS | No issue detected | (IOS)No issue on selecting country code |  | 1.0.0 (12) | No issue detected
Allow the user to input zero at the beginning in mobile number field | Fail | IOS | putting 0 on front mobile number issue.mp4 | (IOS)0 on front mobile number issue |  | 1.0.0 (12) | The app allows inputting a 0 at the beginning, but when saved, the 0 disappears.
Mobile number must also have a verification process | Fail | IOS |  |  |  | 1.0.0 (12) | The current app only supports email verification
Booking of other users can be seen by different users | Pass | IOS | No issue detected | (IOS)(Fixed) Booking of other users can be seen |  | 1.0.0 (12) | This issue is already fixed on the latest version 1.0.0 (10)

## CUSTOMER
To Test | Platform | Prev. Issue | Issue Description | Attachment (Android) | Attachment (IOS) | QA Comments | Dev Comment | Last Re-test | Status (Prod) April 25, 2025 | Louise - (Prod) Android Apr 25 | Status (Prod) April 7 2025 | 1.0.0 (Prod) (Feb 7) | Bry - 1.0.0 (Prod) (IOS) | Jerome - 1.0.0 (PROD) (iOS) Feb 07 | 1.0.0 (17) | Bry - 1.0.0 (17) (IOS) | Jerome - 1.0.0 (17) (iOS) | Joseph - 1.0.0 (Android) | Louise - 1.0.0 (Android) | 1.0.0 (Prod) (Jan 31) | Louise - 1.0.0 PROD (Android) | Joseph - 1.0.0 PROD (Android) | 1.0.0 (16) | Jerome - 1.0.0 (16) iOS | Bry - 1.0.0 (16) (IOS) | 1.0.0 (14) | 1.0.0 (13) | 1.0.0 (12) | 1.0.0 (11) | 1.0.0 (10) | 1.0.0 (9) | 1.0.0 (8)
Create account as user | Both | [6 empty] | 2025-04-25 |  | Pass | Pass |  | Pass |  | Pass |  |  | Pass |  | Pass | Pass | Pass | [5 empty] | Pass | Pass | Pass | Pass | Pass
Update profile as user | Both | First Name Value is the same value as Last Name | [5 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
Update profile as user | Both | Upload photo working but can't save profile picture/takes too long to load | [5 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
Update profile as user | Both |  | Phone number country code not saving | phone number not saving.jpg | (IOS) Phone number country code not saving.mp4 |  |  | 2025-04-25 |  | Pass | Pass |  | Fail | Pass | Fail | Fail | Fail | Pass | Fail | Fail | Fail | Fail | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail
⁠Add address as user | Both | Still having the crash issue (Reinstalled already) | [5 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
⁠Add address as user | Both | After filling out the home details fields and clicking submit, nothing happens, and the data is not saved. | [5 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass |  |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
Create an order as user | Both | Address needed (Cannot perform due to the blocker on the above 1 issues on IOS) | [5 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
Booking Status (Does it change) | Both | [6 empty] | 2025-04-25 |  | Pass | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
My Bookings | Both | Still displaying other users booking | [5 empty] | 2025-04-07 |  |  | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail
App logging out sometimes when reopening the app and no user is showing when closed and opened again | Both | [6 empty] | 2025-04-07 |  |  | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail
Deleting Address | Android | Delete address not working.mp4 | There is no delete button | No delete button.mp4 |  |  |  | 2025-04-07 |  |  | Fail |  | Pass | Pass | Fail | Pass | Pass | Fail | Fail | Fail | Fail | Fail | Pass | Pass | Pass | Pass | Fail | Fail | Fail
Editing Address | Both | Edit button not working.mp4 | Edit button is not working | Edit button not working | (IOS) No edit button.jpg |  |  | 2025-04-07 |  |  | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Forgot Password | Both |  | Reset password email not sending to the email provided | Reset password not sending email.mp4 | forgot pass not sending email.MP4 |  |  | 2025-04-07 |  |  | Pass |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Log in | Both | [6 empty] | 2025-04-07 |  |  | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
Logout | Both | [6 empty] | 2025-04-07 |  |  | Pass

## CLEANER
Test Cases | Platform | Prev. Issue | Issue Description | Attachment (Android) | Attachment (IOS) | QA Comments | Dev Comment | Last Re-test | Status (Prod) April 7 2025 | 1.0.0 (Prod) (Feb 7) | Bry - 1.0.0 (Prod) IOS | Jerome - 1.0.0 (prod) IOS | Joseph - 1.0.0 (Prod) Android | Louise - 1.0.0 (Prod) Android | 1.0.0 (Prod) (Feb 5) | Bry - 1.0.0 PROD (Android) | Jerome - 1.0.0 PROD (iOS) | Joseph - 1.0.0 PROD (Android) | Louise - 1.0.0 PROD (Android) | 1.0.0 (Prod) (Jan 31) | Bry - 1.0.0 PROD (IOS) | Jerome - 1.0.0 PROD (IOS) | Louise - 1.0.0 PROD (Android) | Louise - 1.0.0 PROD (Android) | 1.0.0 (12) | 1.0.0(11) | 1.0.0(10) | 1.0.0 (9) | 1.0.0 (8) | 1.0.0 (7)
Create account | Both | [6 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
Account verification email | Both | [6 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
Forgot password | Both |  | Production version - forgot password not sending link to email provided |  |  |  |  | 2025-04-07 | Pass |  | Pass | Pass | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Create profile | Both | Create Profile: Text Field is a Password Field instead of just a normal textfield for Zip | [5 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pending | Fail
Update profile | Both |  | Cannot Update Profile Information | Cannot update Profile.mp4 | (IOS) Unable to update overall profile.mp4 |  |  | 2025-04-07 | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Update profile | Both |  | The profile picture is not displaying in the Profile Information section. | Profile pic not on profile info.mp4 | (IOS) Unable to update profile picture.mp4 |  |  | 2025-04-07 | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Update profile | Both |  | The Gender and BirthDate input during creation of account is not saved as default on the Profile information, | Date of birth and gender as default issue.jpg | (IOS) Gender and Bday inputted during creation not displaying.jpg |  |  | 2025-04-07 | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Update profile | Both |  | Mobile number created from Create Profile not saved | update button not working.mp4 | (IOS) Contact number inputted during creation not displaying.jpg |  |  | 2025-04-07 | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail
Cleaner app login | Both | [6 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
⁠Cleaner app see job assigned | Both | (IOS) Viewing Jobs Issue.mp4 | [5 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Pass | Pass | Pass
Cleaner accept job | Both | [6 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Pass | Pending | Pending
⁠Cleaner see accepted job on schedule | Both | (IOS) Wrong time text format.jpg | [5 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Fail | Fail | Pending | Pending
Cleaner reject job | Both |  | Wrong text on rejecting booking confirmation dialog: - No keep it -> Yes - Yes, Cancel -> No |  | (IOS) Wrong booking cancellation confirmation dialog.mp4 | Baliktad yung text sa confirmation button |  | 2025-04-07 | Fail |  | Fail | Fail | Pass | Pass | Fail | Fail | Pending | Pass | Pass | Fail | Fail | Fail | Fail | Pass | Fail | Fail | Fail | Fail | Pending | Pending
Home Screen Viewing of Assigned Job | Both |  | Showing Gray Block of Error on Displaying Assigned Job (Home Screen) | (Android)(Home Screen)Gray block of error.mp4 | (IOS) (Home Screen) Gray block of error.mp4 |  |  | 2025-04-07 | Fail |  | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Fail | Pass | Fail
Navigate to my availability page | Both |  | "My availability" page not loading, need to change page then go back to "my availability" page to display the list |  | my availability issue.mp4 |  |  | 2025-04-07 | Fail |  | Fail | Fail | Pass | Pass | Fail | Fail | Fail | Pass | Pass | [5 empty] | Fail
Cleaner Add Availability | Both |  |  |  | (Android) No Plus Icon Availability.jpg |  |  | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Fail | Fail | Pass | Pass | Pass | [5 empty] | Pass
Cleaner Edit Availability | Both | [6 empty] | 2025-04-07 | Pass |  | Pass | Pass | Pass | Pass | Pass | Pass |  | Pass | [6 empty] | Pass

## Test Cases
To Test | Platform | Status | Issue Description | Attachment | QA Comments
Create account as user
Update profile as user
⁠Add address as user
Create an order as user
Admin web signup | Web | Fail
Admin web app log in | Web | Pass
Admin web forgot password | Web | Pending
Admin see order on orders list | Web
Admin see order details | Web
⁠Admin assign cleaner | Web
Cleaner app login
Cleaner app create profile
⁠Cleaner app see job assigned
Cleaner accept job
⁠Cleaner see accepted job on schedule
User app see order accepted
Admin web app see order status update